## Backlog
Order No | Work Item Type | Title | Description | Activity | Estimated Hours
1 | Epic | KUKA FM Middleware | Middleware between an upstream system and KUKA AMR Fleet Manager: dispatch/cancel missions, sync mission and robot states, web UI.
1.1 | Feature | Mission Management | Dispatching, cancelling and monitoring missions created by the middleware (UC1–UC5).
1.1.1 | User Story | UC1 Dispatch mission | As an operator I want to dispatch a new RACK_MOVE mission to a selected robot.
1.1.1.1 | Task | Endpoint POST /api/missions + input validation | Create POST /api/missions. Validate start node, target node, container code, priority (1–99) and that the robot exists. Return 201 or a validation error. | Backend | 6
1.1.1.2 | Task | DB: insert mission | Persist the new mission with status 10 (Created), generated mission_code/request_id and robot FK. Write only after KUKA FM confirms success. | Backend | 4
1.1.1.3 | Task | KUKA FM: submitMission call (RACK_MOVE) | Call submitMission at https://kukafm.its.fei with Authorization token. Build RACK_MOVE body (missionData start/target node, robotIds); other params from appsettings. Handle success=false. | Backend | 6
1.1.1.4 | Task | Dispatch dialog + robot select | Dialog opened by '+ Dispatch mission' with robot select (robots from DB), start/target node, container code and priority. Show success or error message. | Frontend | 6
1.1.1.5 | Task | Unit tests for dispatch mission | Unit tests for input validation, KUKA submitMission request mapping and service logic (KUKA client and DB mocked). | Testing | 6
1.1.2 | User Story | UC2 Cancel mission | As an operator I want to force-cancel a running mission.
1.1.2.1 | Task | Endpoint POST /api/missions/{code}/cancel | Create POST /api/missions/{code}/cancel. Return 200 on success, 404 if not found, 409 if mission is not active. | Backend | 4
1.1.2.2 | Task | DB: load mission + active status check | Load mission by mission_code and check that its status is active (10, 20, 25, 28, 50). | Backend | 2
1.1.2.3 | Task | KUKA FM: missionCancel call (FORCE) | Call missionCancel with missionCode and cancelMode FORCE. Final status (31 Cancelled) is stored later by mission sync. | Backend | 4
1.1.2.4 | Task | Cancel button + confirm dialog | Cancel button shown only on active missions; confirmation dialog mentioning FORCE cancel; show result message. | Frontend | 3
1.1.2.5 | Task | Unit tests for cancel mission | Unit tests for active / not-active / not-found cases and KUKA FM error handling (KUKA client and DB mocked). | Testing | 4
1.1.3 | User Story | UC3 View mission status | As an operator I want to see the current status of active and finished missions.
1.1.3.1 | Task | Endpoint GET /api/missions (active/finished filter) | Create GET /api/missions with optional filter state=active¦finished; return missions with status code and name, robot and timestamps. | Backend | 3
1.1.3.2 | Task | DB: missions query | EF Core query over mission table with status filter, robot join and ordering by created_at desc. | Backend | 2
1.1.3.3 | Task | Missions table + filter + 1 s polling | Missions table (code, status badge, robot, nodes, container, priority, times) with All/Active/Finished filter and auto-refresh every 1 s. | Frontend | 8
1.1.3.4 | Task | Unit tests for view mission status | Unit tests for the active/finished filter logic and the missions service. | Testing | 3
1.1.4 | User Story | UC4 View mission status history | As an operator I want to see all previous statuses of a mission.
1.1.4.1 | Task | Endpoint GET /api/missions/{code}/history | Create GET /api/missions/{code}/history returning previous states (status, robot, valid_from, valid_to). | Backend | 2
1.1.4.2 | Task | DB: mission history query | Query mission_status_history by mission_id ordered by valid_to desc. | Backend | 2
1.1.4.3 | Task | Show history rows in missions table | 'Show history' checkbox adds grey previous-state rows under each mission. | Frontend | 4
1.1.4.4 | Task | Unit tests for view mission status history | Unit tests for the mission history service (existing/unknown mission). | Testing | 2
1.1.5 | User Story | UC5 Synchronize mission status | As the system I want to periodically sync statuses of tracked missions from KUKA FM.
1.1.5.1 | Task | Scheduler job for mission sync (interval from appsettings) | Hosted background service running on interval from appsettings; starts only after first robot sync finished; logs to Seq. | Backend | 4
1.1.5.2 | Task | DB: update mission + write status history | For each changed mission copy previous state into mission_status_history, update status/robot/updated_at; set completed_at for final statuses. | Backend | 4
1.1.5.3 | Task | KUKA FM: jobQuery call (once per tick) | Call jobQuery once per tick (limit and filters from appsettings) and match results to active missions by jobCode. | Backend | 5
1.1.5.4 | Task | Unit tests for mission sync | Unit tests for sync logic: status change, no change, final status, unknown jobCode and KUKA FM error. | Testing | 5
1.2 | Feature | Robot Management | Monitoring robots and their states synchronized from KUKA FM (UC6–UC8).
1.2.1 | User Story | UC6 View robot status | As an operator I want to see all robots and their current state.
1.2.1.1 | Task | Endpoint GET /api/robots + status mapping (Available/Busy/Offline) | Create GET /api/robots returning robots with KUKA status and mapped state (Idle→Available; Departure/Executing/Charging/Updating→Busy; Offline/Abnormal→Offline). | Backend | 3
1.2.1.2 | Task | DB: robots query | EF Core query over robot table ordered by robot_code. | Backend | 2
1.2.1.3 | Task | Robots table + 1 s polling | Robots table (code, type, state badge, KUKA status, battery bar, map, node, mission, updated) with auto-refresh every 1 s. | Frontend | 6
1.2.1.4 | Task | Unit tests for view robot status | Unit tests for status mapping (Available/Busy/Offline) and the robots service. | Testing | 3
1.2.2 | User Story | UC7 View robot status history | As an operator I want to see all previous states of a robot.
1.2.2.1 | Task | Endpoint GET /api/robots/{id}/history | Create GET /api/robots/{id}/history returning previous states with valid_from/valid_to. | Backend | 2
1.2.2.2 | Task | DB: robot history query | Query robot_status_history by robot_id ordered by valid_to desc. | Backend | 2
1.2.2.3 | Task | Show history rows in robots table | 'Show history' checkbox adds grey previous-state rows under each robot. | Frontend | 3
1.2.2.4 | Task | Unit tests for view robot status history | Unit tests for the robot history service (existing/unknown robot). | Testing | 2
1.2.3 | User Story | UC8 Synchronize robot status | As the system I want to periodically sync all robots from KUKA FM.
1.2.3.1 | Task | Scheduler job for robot sync (runs before mission sync on startup) | Hosted background service on interval from appsettings; runs first on startup and signals mission sync to start. | Backend | 4
1.2.3.2 | Task | DB: insert/update robot + write status history | Insert new robots; for every changed robot copy previous state into robot_status_history and update current values. | Backend | 4
1.2.3.3 | Task | KUKA FM: robotQuery call | Call robotQuery without filters to get all robots; map response fields to robot entity. | Backend | 4
1.2.3.4 | Task | Unit tests for robot sync | Unit tests for sync logic: new robot, changed robot, unchanged robot and KUKA FM error. | Testing | 5
1.3 | Feature | Deployment | Containerization, CI and CD of the whole application on the local Azure DevOps Windows agent with Docker Desktop.
1.3.1 | User Story | Containerize application | As a team we want the application to run fully in Docker containers.
1.3.1.1 | Task | Backend Dockerfile (multi-stage .NET build) | Multi-stage Dockerfile: build and publish with .NET SDK image, run on ASP.NET runtime image. | Deployment | 3
1.3.1.2 | Task | Frontend Dockerfile (Angular build + nginx image) | Multi-stage Dockerfile: build Angular app with Node image, serve static files from nginx image. | Deployment | 3
1.3.1.3 | Task | nginx config: serve SPA + proxy /api to backend | nginx.conf serving SPA with fallback to index.html and reverse proxy /api to the backend container. | Deployment | 2
1.3.1.4 | Task | docker-compose: api, web, postgres, seq with volumes | Compose file with web (8080), api (internal only), postgres (5432) and seq (5341) with persistent volumes; images always built. | Deployment | 4
1.3.1.5 | Task | Environment configs | appsettings.Development.json with root/password DB credentials; Production values injected by the pipeline. | Deployment | 3
1.3.2 | User Story | CI pipeline | As a team we want every change built, checked and tested automatically.
1.3.2.1 | Task | ci.yml: build backend + frontend | Azure Pipelines YAML building backend and frontend; agent pool and name taken from pipeline variables. | Deployment | 3
1.3.2.2 | Task | NuGet vulnerability check | Fail the build when vulnerable NuGet packages are found. | Deployment | 2
1.3.2.3 | Task | npm audit check | Run npm audit on the frontend and fail on high/critical vulnerabilities. | Deployment | 1
1.3.2.4 | Task | Run backend tests + publish results | Run dotnet test for backend unit tests and publish test results to the pipeline. | Deployment | 2
1.3.3 | User Story | CD pipeline (local Docker) | As a team we want successful builds deployed automatically to local Docker.
1.3.3.1 | Task | cd.yml | Azure Pipelines YAML used for deployment. Manual run only (trigger: none). | Deployment | 2
1.3.3.2 | Task | Generate appsettings.Production.json from pipeline variables | Create appsettings.Production.json from secret pipeline variables (KUKA FM token, DB credentials). | Deployment | 3
1.3.3.3 | Task | docker compose build + up -d on agent Docker Desktop | Run docker compose build and up -d on the agent host's Docker Desktop (Linux containers). Include docker builder prune -af to cleanup used resources. | Deployment | 3
1.3.3.4 | Task | Apply DB migrations on API startup | API applies EF Core migrations on startup (Database.Migrate()) so every deployment updates the PostgreSQL schema; no migration step in the pipeline. | Backend | 2
1.3.3.5 | Task | Smoke check after deployment (frontend + /api) | After deploy verify that the frontend (8080) and /api through nginx respond; fail the pipeline otherwise. | Deployment | 2
Note on F1: Task hours are example estimates for one developer. Epic / Feature / User Story hours are SUMIFS roll-ups of their tasks.

## Summary
Estimated hours by Feature
Feature | Hours
Mission Management
Robot Management
Deployment
Total
Estimated hours by Activity
Activity | Hours
Backend
Frontend
Testing
Deployment
Total